## Slide 1: Amendments to grant agreements
CDG Quality and Promotion, 30 June 2017
Notes: Reasons that led to adding this point to the agenda
Queries received…
One MS suggested the discussion
GAs for SPs and for MPs contain same provisions, in particular with regard eligible costs, budget transfer, amendments; Therefore we should strive to have same interpretation and thus application of them
NB The decision on the amendments is at the discretion of the Member State competent authorities

## Slide 2: Guiding Principles
  The general terms and conditions of the GA can NOT be changed via an amendment. Only GA-specific data (e.g. duration of the reporting periods, starting date, etc.) and the options in the GA can be added, removed or updated via an amendment
  Amendments may NOT result in changes that — if known before awarding the grant — would have had an impact on the award decision.
Notes: NB
Art 10(6) of IR: Where appropriate, Member States may amend certain terms in the model contracts in order to comply with their national law, provided that this does not infringe Union legislation.
Art 14(1) of the GA for SPs: 14.1. Obligation to submit deliverables
[OPTION by default: The coordinator must submit the ‘deliverables’ identified in Annex 1.]
[OPTION if a Member State would require continuous monitoring: The coordinator must submit the ‘deliverables’ identified in Annex 1 in accordance with the timing and conditions set out in Annex 8.]
Amendments may NOT result in changes that — if known before awarding the grant — would have had an impact on the award decision.
Thus the changes that would e.g.:
an impact on the eligibility criteria
involve changes to the programme and/or its budget and affect the award criteria announced in the work programme/call (e.g. the tasks in Annex 1 are changed so substantially that the programme no longer corresponds to the scope of the call)
- Subject of Art 39 of the GA, presented on the next slide

## Slide 3: Article 39 of the GA - Amendments
  A grant means Union's financial contribution to one or more beneficiaries for the purpose of carrying out the selected programme.
    Since the approved programme is an integral part of the GA, the undertakings it contains are binding on the beneficiary
  programme proposals are selected for Union's financial contribution on the basis of the proposed activities including the deliverables specified and the predicted results
  Art 39 of the GA: an amendment cannot call into question the decision awarding the grant or breach the principle of equal treatment of applicants
Notes: Amendments may NOT result in changes that — if known before awarding the grant — would have had an impact on the award decision. Those are mostly changes that:
 involve the consortium composition and have an impact on the eligibility criteria set out in General Annexes A and C to the Main Work Programme (e.g. consortium of three entities established in three different Member States (BG, PL and FR) and replacement of the PL beneficiary by a BG beneficiary while the call required the representation in the consortium of at least three Member States)
 involve changes to the action and/or its budget and affect the award criteria announced in the work programme/call (e.g. the tasks in Annex 1 are changed so substantially that the action no longer corresponds to the scope of the call)
 breach the principle of equal treatment of applicants
 do not comply with the rules applicable to the GA (i.e. Financial Regulation No 966/2012, Rules for Participation Regulation No 1290/2013, etc.) or with provisions of the GA itself (e.g. amendment to subcontract tasks of the coordinator).
(► amendments to the grant agreement that involve modifications of the programme should be concluded cautiously/ sparingly /thoughtfully…)

## Slide 4: Article 4.2 of the GA: Budget transfers
  the estimated budget breakdown indicated in the programme proposal (Annex 2 to the GA) may be adjusted during the implementation — without an amendment — by transfers of amounts between budget categories and between beneficiaries in case of multi beneficiary programme, if the action is implemented as described in the programme (Annex 1 to the GA).
    Beneficiaries may not add costs relating to subcontracts that are not provided for in Annex 1, unless such additional subcontracts are approved by an amendment
  If the budget transfer is due to a significant change in Annex 1, an amendment to the GA is needed.
Notes: What can be transferred?
If the incurred eligible costs are lower than the estimated eligible costs, the difference can be allocated to another beneficiary or another budget category. The amount reimbursed for the other beneficiary (by application of its reimbursement rate) or for the other budget category (to which the budget transfer is intended) may thus be higher than planned.
What not?
The GA allows transfers of budget, not of tasks.
A beneficiary cannot transfer budget to a form of costs that it did not set out in its estimated budget — except within the personnel costs category.

## Slide 5: Significant change of the programme
  Amendment needed (in particular):
  significant change of the programme e.g. if tasks are added to/removed from the programme or of their division among the beneficiaries
  changes to Annex 2 (estimated budget) e.g. a budget transfer of amounts between beneficiaries or between budget categories (or both) which are linked to a significant change in the programme in Annex 1
  NB Article 39 of the GA
Notes: A significant change is a change that affects the activities included in the programme in Annex 1 to the GA
Change of Annex 1 (programme) would involve/require the change/update of Annex 2 (estimated budget)
NO amendment is needed: Transfers of amounts between beneficiaries or between budget categories (or both) do NOT require an amendment, provided that the action is implemented in line with Annex 1

## Slide 6: Conclusions
  amendments to the grant agreement that involve modifications of the programme should be concluded only if necessary & possible
  at the time of reporting, beneficiaries may declare costs that are different from the estimated eligible costs in the budget
    If the incurred eligible costs are lower than the estimated eligible costs, the difference can be allocated to another beneficiary or another budget category. The amount reimbursed for the other beneficiary or for the other budget category may thus be higher than planned
    NB Art 27 – Reduction of the grant
Notes: ► amendments to the grant agreement that involve modifications of the programme should be concluded cautiously/ sparingly /thoughtfully
  the budget in Annex 2 to the grant agreement is an estimation. Therefore at the time of reporting, beneficiaries may declare costs that are different from the estimated eligible costs in the budget.
  When beneficiaries declare eligible costs in the payment requests, they are required to submit 'technical reports' which describe the activities set out in the programme were implemented and what results have been achieved by using the indicators identified in the programme. Beneficiaries have to explain any differences between the activities and their outcomes that are planned or expected and those actually carried out or obtained (cf. Article 15 of the GA).
ARTICLE 27 — REDUCTION OF THE GRANT
The Member State may — at the payment of the balance or afterwards — reduce the maximum grant amount (see Article 5.1), if a beneficiary (or a natural person who has the power to represent or take decisions on its behalf) has committed substantial errors, irregularities or fraud or serious breach of obligations under the Agreement or during the award procedure (including improper implementation of the action, submission of false information, failure to provide required information, breach of ethical principles).

## Slide 7
Thank you for your attention.
Questions?
Notes: point to be discussed on the next MANCOM(s)?