## Slide 1
Action Plan for the future of
organic production in the
European union
State of Play
<number>
Notes: <number>

## Slide 2: Action Plan on the future of Organic Production in Europe (short summary)
Notes: <number>

## Slide 3: Competitiveness Information on CAP Instruments
  Recommendation on use of RD funds, Common Fisheries Policy
    End of 2015, adoption of 118 RD programme. All but NL included OF. NL used state aids
    Unit actively involved in the analysis and future modifications.
  Informative documents
  - see leaflet
  Inclusion of organic farming as a specific theme in calls for tender for information measures
    Done for 2014 calls
  Raising awareness on promotion instruments
    Ongoing
Notes: <number>

## Slide 4: Competitiveness Awareness of EU scheme and logo
  Periodical surveys on consumers awareness of the logo
    Takes place every two years through the Eurobarometer; in 2015 last survey. Data is available on line as from January 2016.
    Repetition of Questions so as to see the evolution/trend
  Survey on consumers awareness and confidence in and understanding of the scheme
    Preparation ongoing
    Date still to be decided
  Revision of Green Public Procurement criteria
    Study carried on by JRC
    First meeting of the ad-hoc working group in Jan 2016.
    Revised GPP criteria for food and catering planned to be adopted end of 2016
Notes: <number>

## Slide 5: Competitiveness Research and Innovation
  Recommendation to stakeholders to set up a database on availability of organic seeds.
    Similar initiatives encouraged for aquaculture.
    Workshops and conferences
  Conference on research and innovation priorities - Expo Milano – May 2015
    Very successful event
    Wide participation
    The results will fit into the H2020 work programme
  Organic in Horizon 2020
    Close collaboration with other Commission teams for the preparation of the work programme
    Organic is increasingly present and visible
Notes: <number>

## Slide 6: Competitiveness Research and Innovation
  Regular facts and figures on organic production
    During 2014 and 2015: enhanced collaboration with EUROSTAT and simplification of the questionnaire;
    Results: more statistics available and published on EUROSTAT's website (by November 2015, all MS provided – at least some - data).
    Ongoing work: clarification of definitions in order to improve data quality and consistency.
    New doc issued early next year
Notes: <number>

## Slide 7
  Study on the added-value along the organic food supply chain
  Survey on the attractiveness of the organic scheme for small farmers
    In preparation – foreseen for 2017

## Slide 8: Distribution of the added value along the organic food chain.
    Study launched in 2015, 2 offers received in September 2015 and study completed by end of 2016.
    Contractor: Thuenen Institute of Farm Economics.
Theme 1: How much added value is generated by the organic food supply chain and who are the market players benefiting from it?
Theme 2: How is the added value distributed among market players in the supply chain
Theme 3: What factors influence the formation and distribution of added value for each relevant actor in the supply chain, including agricultural producers?

## Slide 9: Distribution of the added value along the organic food chain.
The results indicate that organic producers get higher farm gate prices than conventional but the producers’ share of added value remains relatively low

## Slide 10: Consumer awareness
  Encourage MS to explore synergies of the accreditation bodies and competent authorities
    Discussion in RCOP
    The revision of guidelines on control is ongoing and will be completed once the new regulation is approved
  Liaising with Acreditation Bodies for Control Bodies in Third Countries
    Participate in major events with relevant partners
  Integration of organic production legislation in the TARIC database
    Preparatory action have been finalised in close collaboration with DG TAXUD and MS
    Need to finalise the elettronic certification
    Likely to be completed in 2016
Notes: <number>

## Slide 11: Consumer awareness
  Electronic certification for imports
    electronic certificate ready in TRACES for January 2016;
    amendments of Regulation No 1235/2008 are being discussed with MS
    the e-certificate to be used once the amended regulation enters into force (transitional period foreseen)
  Electronic certification for internal market
    Kick off development in early 2016 . Operational in 2018
    Objective: to create a publicly available database on organic certificates
    Documentary evidence translated into IT tools + some new features.
  Targetted workshops to assist MS with fraud prevention policy
    Liaising with SANTE (Food Fraud Network) and OLAF
    HLConference on fraud controls July 2015, Milan.
    IT tool, administrative assistance and coopération system, fall 2017.
  Compedia/casebook of fraud cases
    Closely working with SANTE Food Fraud Network, FVO and OLAF
    will follow (2017)
Notes: <number>

## Slide 12: External dimension
  Support and cooperate with trade partners from developing countries
    Liaising with DEVCO; first results are appearing
  Plurilateral agreement among leading organic partners in the World
    Long term process
    A priority to lead the agenda for convergence of standards
  Statistical data on trade with third countries
    A study to be carried out "analysis of EU trade of organic products"
  Codex Alimentarius
    Aquaculture
    Organic wine rules
  Aim to increase protection of EU organic logo in 3rd countries
  - Protection of EU logo in international agreement
Notes: <number>

## Slide 13: Conclusion
Medium term process (2014-2020)
We are making important progress
A strategic framework for the sector, a major priority for the Commission
Notes: <number>

## Slide 14: Available at : http://ec.europa.eu/agriculture/organic/eu-policy/european-action-plan/index_en.htm
Notes: <number>

## Slide 15: Electronic COI – results and next steps
Aim of e-COI in TRACES:
  Better traceability
  Better control at imports
  Simpler administrative process
NEW: E-COI ready to use! https://webgate.ec.europa.eu/tracesnt/
Will be adapted to include amendments to R1235/2008
Workshops/trainings:
  Presentation in Biofach – 10-12 Feb 2016
  Workshops with national experts – end Feb 2016
  EOCC training – 11 May 2016
  Next workshop with national experts – Sep 2016